## Projects
key | name | description | platform | start_date | end_date | project_lead_email
HRMS | HR Management System | Complete HR management solution with employee tracking, payroll, and attendance | web | 2025-01-01 | 2025-12-31 | admin@company.com
ECOM | E-Commerce Platform | Online shopping platform with payment integration and inventory management | web | 2025-02-01 | 2025-11-30 | admin@company.com

## Epics
project_key | name | description | start_date | end_date
HRMS | User Management | User authentication, authorization, and profile management | 2025-01-01 | 2025-03-31
HRMS | Employee Management | Employee records, onboarding, and offboarding | 2025-02-01 | 2025-05-31
HRMS | Attendance Tracking | Clock in/out, leave management, and attendance reports | 2025-04-01 | 2025-07-31
ECOM | Product Catalog | Product listing, categories, and search functionality | 2025-02-01 | 2025-04-30
ECOM | Shopping Cart | Cart management, checkout, and order processing | 2025-03-01 | 2025-06-30

## Sprints
project_key | name | goal | start_date | end_date
HRMS | Sprint 1 | Complete user authentication and basic profile | 2025-01-01 | 2025-01-14
HRMS | Sprint 2 | Employee CRUD operations and search | 2025-01-15 | 2025-01-28
HRMS | Sprint 3 | Attendance clock in/out functionality | 2025-01-29 | 2025-02-11
ECOM | Sprint 1 | Product listing and category management | 2025-02-01 | 2025-02-14
ECOM | Sprint 2 | Shopping cart and checkout flow | 2025-02-15 | 2025-02-28

## Features
project_key | epic_name | name | description | priority | status
HRMS | User Management | Login Module | Email/password login with JWT authentication | highest | todo
HRMS | User Management | Registration Module | User registration with email verification | high | todo
HRMS | User Management | Profile Management | User profile viewing and editing | medium | todo
HRMS | Employee Management | Employee CRUD | Create, read, update, delete employee records | highest | todo
HRMS | Employee Management | Employee Search | Search and filter employees by various criteria | high | todo
HRMS | Attendance Tracking | Clock In/Out | Employee time tracking with clock in/out | highest | todo
ECOM | Product Catalog | Product Listing | Display products with images and details | highest | todo
ECOM | Shopping Cart | Cart Management | Add, remove, update items in cart | highest | todo

## Issues
project_key | epic_name | feature_name | sprint_name | type | name | description | priority | status | assignee_email | story_points | estimated_hours
HRMS | User Management | Login Module | Sprint 1 | story | Implement Login API | Create POST /auth/login endpoint with JWT token generation | highest | todo | dev@company.com | 5 | 8
HRMS | User Management | Login Module | Sprint 1 | story | Create Login UI | Design and implement login form with validation | high | todo | frontend@company.com | 3 | 6
HRMS | User Management | Registration Module | Sprint 1 | story | User Registration API | Create POST /auth/register endpoint with email verification | high | todo | dev@company.com | 5 | 10
HRMS | Employee Management | Employee CRUD | Sprint 2 | story | Create Employee API | POST endpoint to create new employee records | highest | todo | dev@company.com | 3 | 5
HRMS | Employee Management | Employee CRUD | Sprint 2 | story | List Employees API | GET endpoint with pagination and filtering | high | todo | dev@company.com | 3 | 4
HRMS | Employee Management | Employee Search | Sprint 2 | task | Implement Search Algorithm | Add search functionality for employee names and IDs | medium | todo | dev@company.com | 2 | 3
HRMS | Attendance Tracking | Clock In/Out | Sprint 3 | story | Clock In API | POST endpoint to record clock in time | highest | todo | dev@company.com | 3 | 5
HRMS | Attendance Tracking | Clock In/Out | Sprint 3 | story | Clock Out API | POST endpoint to record clock out time and calculate hours | highest | todo | dev@company.com | 3 | 5
ECOM | Product Catalog | Product Listing | Sprint 1 | story | Product API | CRUD endpoints for product management | highest | todo | dev@company.com | 5 | 8
ECOM | Product Catalog | Product Listing | Sprint 1 | story | Product Display UI | Grid view of products with images and prices | high | todo | frontend@company.com | 5 | 10
ECOM | Shopping Cart | Cart Management | Sprint 2 | story | Add to Cart API | POST endpoint to add items to cart | highest | todo | dev@company.com | 3 | 5
ECOM | Shopping Cart | Cart Management | Sprint 2 | story | Cart UI | Display cart items with quantity controls | high | todo | frontend@company.com | 3 | 6

## Subtasks
project_key | parent_issue_name | name | description | priority | status | assignee_email | estimated_hours
HRMS | Implement Login API | Design database schema | Create users table with necessary fields | high | todo | dev@company.com | 2
HRMS | Implement Login API | Write authentication logic | Implement password hashing and JWT generation | highest | todo | dev@company.com | 4
HRMS | Implement Login API | Add input validation | Validate email format and password strength | medium | todo | dev@company.com | 1
HRMS | Create Login UI | Design mockup | Create UI mockup in Figma | high | todo | designer@company.com | 2
HRMS | Create Login UI | Implement form | Build login form with React | high | todo | frontend@company.com | 3
HRMS | Create Employee API | Design employee schema | Define employee model with all required fields | high | todo | dev@company.com | 1.5
HRMS | Create Employee API | Implement validation | Add validation for employee data | medium | todo | dev@company.com | 1.5
ECOM | Product API | Design product schema | Create product model with categories | high | todo | dev@company.com | 2
ECOM | Product API | Add image upload | Implement image upload functionality | medium | todo | dev@company.com | 3