## Projects
key | name | description | platform | start_date | end_date | project_lead_email
DQZ | DigiAI Quest – Daily Quiz | Daily Quiz feature aligned to MOM with detailed FE/BE/Admin tasks | Android | 2025-12-22 | 2025-12-31

## Epics
project_key | name | description | start_date | end_date
DQZ | Daily Quiz Experience | User-facing quiz flow | 2025-12-22 | 2025-12-25
DQZ | User Registration & Eligibility | Mandatory profile & eligibility | 2025-12-22 | 2025-12-25
DQZ | Quiz Rules & Validation | Timer, attempt & scoring rules | 2025-12-22 | 2025-12-26
DQZ | Rewards & Wallet | Prize & wallet credit | 2025-12-23 | 2025-12-27
DQZ | Admin Panel – Quiz Management | Admin quiz, question & prize | 2025-12-23 | 2025-12-28
DQZ | Notifications & Reports | Reminder & reports | 2025-12-24 | 2025-12-29
DQZ | QA & Release | Testing & deployment | 2025-12-28 | 2025-12-31

## Features
project_key | epic_name | name | description | priority | status
DQZ | Daily Quiz Experience | Daily Quiz Entry | Home screen Daily Quiz CTA | High | todo
DQZ | Daily Quiz Experience | Timed Quiz | 1-minute timed quiz | High | todo
DQZ | User Registration & Eligibility | Mandatory Form | User details before quiz | High | todo
DQZ | Quiz Rules & Validation | One Attempt Rule | One quiz per day | High | todo
DQZ | Rewards & Wallet | Prize Logic | Reward for 10/10 score | High | todo
DQZ | Admin Panel – Quiz Management | Admin Quiz Setup | Create quiz/questions/prizes | High | todo
DQZ | Notifications & Reports | Notifications | Daily reminder & result | Medium | todo

## Issues
project_key | epic_name | type | name | description | priority | status | assignee_role | story_points | estimated_hours
DQZ | Daily Quiz Experience | Story | Daily Quiz Access | User can access Daily Quiz from home screen | High | todo |  | 5 | 8
DQZ | Daily Quiz Experience. | Story | Timed Quiz Attempt | User attempts quiz within time limit | High | todo |  | 5 | 8
DQZ | User Registration & Eligibility | Story | Mandatory User Form | User must submit profile before quiz | High | todo |  | 5 | 8
DQZ | Quiz Rules & Validation | Story | Single Attempt Validation | System restricts multiple attempts | High | todo |  | 5 | 8
DQZ | Rewards & Wallet | Story | Reward Distribution | System rewards full scorers | High | todo |  | 5 | 8
DQZ | Admin Panel – Quiz Management | Story | Admin Quiz Management | Admin manages quiz/questions/prizes | High | todo |  | 5 | 8
DQZ | Daily Quiz Experience | Task | Home Screen Update | Replace Services button with Daily Quiz CTA | Medium | todo |  |  | 6
DQZ | Daily Quiz Experience | Task | Quiz UI Development | MCQ UI, navigation & submit | Medium | todo |  |  | 8
DQZ | Daily Quiz Experience | Task | Timer Integration | Countdown timer with auto submit | Medium | todo |  |  | 6
DQZ | User Registration & Eligibility | Task | User Form UI | Form fields & validation | Medium | todo |  |  | 6
DQZ | Quiz Rules & Validation | Task | Attempt Validation API | Validate one attempt per user per day | Medium | todo |  |  | 6
DQZ | Quiz Rules & Validation | Task | Auto Submit Service | Force submit on timeout | Medium | todo |  |  | 5
DQZ | Rewards & Wallet | Task | Reward Calculation Service | Check score & credit wallet | Medium | todo |  |  | 8
DQZ | Notifications & Reports | Task | Notification Service | Daily reminder & result push | Medium | todo |  |  | 6
DQZ | Admin Panel – Quiz Management | Task | Admin Quiz CRUD | Create/manage quiz, questions & prizes | Medium | todo |  |  | 8
DQZ | QA & Release | Task | Testing & Deployment | Functional testing & release | Medium | todo |  |  | 6

## Subtasks
project_key | parent_issue_name | name | description | priority | status | assignee_role | estimated_hours
DQZ | Home Screen Update | CTA Placement | Add Daily Quiz button | Low | todo |  | 2
DQZ | Quiz UI Development | Option Selection | Answer selection logic | Low | todo |  | 3
DQZ | Timer Integration | Countdown Logic | Timer tick & expiry | Low | todo |  | 3
DQZ | User Form UI | Field Validation | Mandatory field validation | Low | todo |  | 3
DQZ | Attempt Validation API | DB Check | Check attempts by date | Low | todo |  | 3
DQZ | Auto Submit Service | Timeout Handler | Auto-submit payload | Low | todo |  | 3
DQZ | Reward Calculation Service | Wallet Credit | Credit prize wallet | Low | todo |  | 3
DQZ | Admin Quiz CRUD | Question Mapping | Subject-topic-question mapping | Low | todo |  | 3